## Change_List
No | Date | Project Coordinator | Project Name | Change Activity | Impact Site List | Service Type | Down Time | Site Group | Commercial Zone | NCR Number | Change Manager
1 | 2020-11-02 | Sobuz Ahmed_01841122538 | NCCD AbisoIP | E1 deletion & Collect BTS Cable | SYKNG16,SYKNG07,SYGLP08 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet |  | Muhammad Shahed
2 | 2020-11-02 | KM Jiaul Islam Jibon_01847188948 | NCCD AbisoIP P3 | E2E Lease Site Ping Test 1/1 | FPSDR04,FPSDR05,FPSDR09,RJPNG19 | Service Effective | 00:30 Minute | Kustia | e.co_Kustia |  | Muhammad Shahed
3 | 2020-11-02 | Prodip Biswas_01841133479 | L18CellAdd, Y2020 | Jumper Cable Change 1/1 | HGMDB19, MBJRI14, BMSDR24, BMSRL10 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet |  | Sumon Kumar Biswas
4 | 2020-11-02 | Prodip Biswas_01841133479 | L18CellAdd, Y2020 | Take Print Screen from MBB | BMNBG30,BMNNG05,BMNNG09,BMSDR54,BMSRL08,HGAZM09,MBSML28,SYBLG30 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet |  | Sumon Kumar Biswas
5 | 2020-11-02 | Prodip Biswas_01841133479 | L18CellAdd, Y2020 | Take Print Screen from MBB | SYBSW17,SYDKS18,SYDKS21,SYGLP20,SYGLP21,SYGWN13,SYGWN19SYJNT08 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet |  | Sumon Kumar Biswas
6 | 2020-11-02 | Prodip Biswas_01841133479 | L18CellAdd, Y2020 | Take Print Screen from MBB | SYKNG03,SYKNG04,SYKNG12,BMNBG21,SYCMP09 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet |  | Sumon Kumar Biswas
7 | 2020-11-02 | Md. Shafiqur Rahman_01841122531 | Relocation | FE Configure, Site name change | DHTIA08,DHSBG28 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka Metro |  | Muhammad Shahed
8 | 2020-11-02 | Md. Masudur Rahman_01841122536 | Padma_Colo | Slot Remove for alarm clear | SYGWN03,SYJNT08,SYJNT02 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet |  | Muhammad Shahed
9 | 2020-11-02 | Md. Masudur Rahman_01841122536 | DHAKA_MODERNIZATION | Rectification | NKKND02,MYISG02 | Service Effective | 00:30 Minute | Mymensingh | e.co_Mymensingh |  | Muhammad Shahed
10 | 2020-11-02 | Md. Masudur Rahman_01841122536 | Padma_Colo | Rectification 1/1 | SYKNG05,SYSDR26,SYJNT03,SYJNT08 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet |  | Muhammad Shahed
11 | 2020-11-02 | Md. Masudur Rahman_01841122536 | DHAKA_MODERNIZATION | Dismantle Materials Return | DHDHM33,DHDHM36,MNSNG08 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka North |  | Muhammad Shahed
12 | 2020-11-02 | Md. Masudur Rahman_01841122536 | Finito | Rectification | DHDHN41,DHTEJ23,DHTIA09,DHRMN05 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka Metro |  | Muhammad Shahed
13 | 2020-11-02 | Md. Masudur Rahman_01841122536 | Padma_Colo | MW Dismantle Link ID:SY07H30759 Link Name:SYJNT03-SYGWN03 DCN Impact :SYJNT03-HRTN-02,SYJNT03-HRTN-03,SYJNT08-HRTN-01,SYGWN03-HRTN-02 DCN Route:SYGWN03-SYJNT03-SYJNT08 WO0000000162410 | SYJNT03,SYGWN03 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet |  | Muhammad Shahed
14 | 2020-11-02 | Md. Masudur Rahman_01841122536 | NCCD AbisoIP | Slot Remove for alarm clear | SYBNB42 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet |  | Muhammad Shahed
15 | 2020-11-02 | Md. Masudur Rahman_01841122536 | NCCD AbisoIP | Traffic Shifting 1/1 | TNNGP12,TNKLH04,JPISL14,SRSDR07 | Service Effective | 00:30 Minute | Mymensingh | e.co_Mymensingh |  | Muhammad Shahed
16 | 2020-11-02 | Md. Masudur Rahman_01841122536 | DHAKA_MODERNIZATION | Dismantle Materials Return | DHKGNT1,MNLHG18,MNSRN18,MNSRK13,MNSRK16,NGSNG11,NGSNG20 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka South |  | Muhammad Shahed
17 | 2020-11-02 | Md. Masudur Rahman_01841122536 | Padma_Colo | Traffic shifting 1/1 | MBJRI11,MBJRI10 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet |  | Muhammad Shahed
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Formulas:
Date = [1]!Table1[[#This Row],[Date]]

## Information (hidden)
Site List | Relation | 30 Minute |  |  | Function for init.py | Project Coordinator | Service Type | Down Time | Dhaka | Barisal | Mymensingh | Kustia | Sylhet | Chittagong | Comilla | Khulna | Noakhali | Rajshahi | Rangpur
DHGUL10 | DHGUL10 | 2020-07-04 | 9:00 | 07/04/2020 9:00 AM | get_start_time | Md. Masudur Rahman | Service Effective | 00:00 Minute | e.co_Dhaka Metro | e.co_Barisal | e.co_Mymensingh | e.co_Kustia | e.co_Sylhet | e.co_CTG_Metro | e.co_Comilla | e.co_Khulna | e.co_Noakhali | e.co_Rajshahi | e.co_Rangpur
DHGUL74 | DHGUL10,DHGUL74 |  | 11:00 | 07/04/2020 11:00 AM | get_start_downtime | KM Jiaul Islam Jibon | Non-Service Effective | 00:30 Minute | e.co_Dhaka North |  |  |  |  | e.co_CTG_North
DHGUL76 | DHGUL10,DHGUL74,DHGUL76 |  | 11:40 | 07/04/2020 11:40 AM | get_end_downtime | Md. Mafuzur Rahman |  | 00:45 Minute | e.co_Dhaka South |  |  |  |  | e.co_CTG_South
DHMRP28 | DHGUL10,DHGUL74,DHGUL76,DHMRP28 |  | 17:00 | 07/04/2020 5:00 PM | get_activity_hour | Md. Shahadat Hossain |  | 01:00 Hour
DHPLB19 | DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19 |  | 18:00 | 07/04/2020 6:00 PM | get_end_time | Prodip Biswas |  | 02:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19, |  |  |  |  | Md. Rashekul Islam Raju |  | 03:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19,, | [6 empty] | 04:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19,,, | [6 empty] | 06:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19,,,, |  |  |  |  | Robi PM |  | 08:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19,,,,, |  |  |  |  | Muhammad Shahed
Ripan Kumar
Md. Walee Zaman
Faisal Mahmud Fuad
Shahriar Mahbub
Sumon Kumar Biswas