## Change_List
No | Date | Project Coordinator | Project Name | Change Activity | Impact Site List | Service Type | Down Time | Site Group | Commercial Zone | NCR Number | Change Manager
1 | 31-Aug-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | New Link installation | MGSNG08,DHKGNT1 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka North | CRQ000000257523 | Muhammad Shahed
2 | 31-Aug-20 | Md. Masudur Rahman | CEP | New Link installation | DHBDDA7,DHTEJ15,DHTEJ07 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000257526 | Muhammad Shahed
3 | 31-Aug-20 | Md. Masudur Rahman | Padma_Colo | New Link installation | BHCFN02,BHCFN26,BHLMN01,BHLMN15 | Non-Service Effective | 00:00 Minute | Barisal | e.co_Barisal | CRQ000000257528 | Muhammad Shahed
4 | 31-Aug-20 | Md. Masudur Rahman | NCCD AbisoIP | Traffic Check for Traffic shiftng | HGNBG28,HGNBG08 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000257530 | Muhammad Shahed
5 | 31-Aug-20 | Md. Masudur Rahman | CEP | New Link installation | DHMDP30,DHMDP39 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000257532 | Muhammad Shahed
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Sheet1
No | Date | Project Coordinator | Project Name | Change Activity | Impact Site List | Service Type | Down Time | Site Group | Commercial Zone | NCR Number | Change Manager
1 | 29-Aug-20 | Prodip Biswas | L18CellAdd, Y2020 | GSM & RRU Swap | SYGLP22,SYDKS25 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000257020 | Sumon Kumar Biswas
2 | 29-Aug-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | New Link installation | MGSNG08,DHKGNT1 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka North | CRQ000000257022 | Muhammad Shahed
3 | 29-Aug-20 | Md. Masudur Rahman | CEP | New Link installation | DHTEJ15,DHTEJ07,DHTIA32,DHTIA11 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000257024 | Muhammad Shahed
4 | 29-Aug-20 | Md. Masudur Rahman | Padma_Colo | New Link installation | MDKLK01,BSMLD12,BHLMN01,BHLMN15 | Non-Service Effective | 00:00 Minute | Barisal | e.co_Barisal | CRQ000000257026 | Muhammad Shahed
5 | 29-Aug-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | New Link installation | MNLHG18,MNSRN18 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka South | CRQ000000257028 | Muhammad Shahed
6 | 29-Aug-20 | Md. Masudur Rahman | CEP | New Link installation | DHMDP30,DHMDP39 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000257030 | Muhammad Shahed
7 | 29-Aug-20 | KM Jiaul Islam Jibon | NCCD_AbisoIP | FE Configuration | RJBLK11,RJPNG02,RJBLK02,PBSDR34,PBSDR37 | Non-Service Effective | 00:00 Minute | Kustia | e.co_Kustia | CRQ000000257032 | Muhammad Shahed
6 | 29-Aug-20 | KM Jiaul Islam Jibon | Dhaka-Modernization | FE Configuration | DHPTN50/DHPTN42, DHPTN41 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000257034 | Muhammad Shahed
| 29-Aug-20 | KM Jiaul Islam Jibon | Dhaka-Modernization | FE Configuration | DHSVRG5 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka South | CRQ000000257036 | Muhammad Shahed
11 | 2020-08-26 | Md. Masudur Rahman | NCCD AbisoIP | Garbage E1 Deletetion | SYBLG09,SYBLG04 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000256044 | Muhammad Shahed
14 | 18-Aug-20 | Md. Masudur Rahman | NCCD AbisoIP | MW Link Dismantle Link ID: SY13E10200 Link Name: SYBNB22-SYBNB30 DCN Impact: SYBNB22-EMTN-01 | SYBNB22,SYBNB30 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000252871 | Muhammad Shahed
15 | 18-Aug-20 | Md. Masudur Rahman | NCCD AbisoIP | MW Link Dismantle Link ID: SY13H17220 Link Name: SYBNB15-SYBNB12 DCN Impact: SYBNB12-HRTN-01,SYBNB15-HRTN-01 | SYBNB15,SYBNB12 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000252874 | Muhammad Shahed
16 | 18-Aug-20 | Md. Masudur Rahman | NCCD AbisoIP | MW Link Dismantle Link ID: SY11H17368 Link Name: HGNBG30-HGNBG03 DCN Impact: HGNBG03-HRTN-05,HGNBG30-HRTN-05 | HGNBG30,HGNBG03 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000252876 | Muhammad Shahed
17 | 18-Aug-20 | Md. Masudur Rahman | NCCD AbisoIP | MW Link Dismantle Link ID: SY13H17174 Link Name:HGNBG04-HGNBG03 DCN Impact: HGNBG04-HRTN-01,HGNBG03-HRTN-06 | HGNBG04,HGNBG03 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000252879 | Muhammad Shahed
18 | 18-Aug-20 | Md. Masudur Rahman | NCCD AbisoIP | MW Link Dismantle Link ID: SY07S00421 Link Name:HGNBG03-SYBLG04 DCN Impact: No Data Found | HGNBG03,SYBLG04 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000252884 | Muhammad Shahed
1 | 26-Aug-20 | Md. Rashekul Islam Raju | Project 964 | GSM Antenna Optimization | SYSDR46,SYGWN03 | Service Effective | 00:45 Minute | Sylhet | e.co_Sylhet | CRQ000000256032 | Muhammad Shahed
2 | 26-Aug-20 | Md. Rashekul Islam Raju | Project 964 | GSM Antenna Optimization | TNGTL08 | Service Effective | 00:45 Minute | Mymensingh | e.co_Mymensingh | CRQ000000256036 | Muhammad Shahed
3 | 26-Aug-20 | Prodip Biswas | L18CellAdd, Y2020 | GSM & RRU Swap | HGSDR36,BMBJN31 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000256038 | Sumon Kumar Biswas
4 | 26-Aug-20 | Prodip Biswas | L18CellAdd, Y2020 | GSM & RRU Swap | HGSDR36,BMBJN31 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000256041 | Sumon Kumar Biswas
5 | 26-Aug-20 | Md. Shahadat Hossain | Padma Colocation Project | CPRI Cable & RRU Swap | SNJGN20,SNDRI06,SNDRI07,SNDRI10 | Service Effective | 04:00 Hour | Sylhet | e.co_Sylhet | CRQ000000256044 | Muhammad Shahed
6 | 26-Aug-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | New Link instalation | MGSNG08,DHKGNT1 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka North | CRQ000000256051 | Muhammad Shahed
7 | 26-Aug-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | PAT activity | TNKLH04,TNNGP12,TNMZP48 | Non-Service Effective | 00:00 Minute | Mymensingh | e.co_Mymensingh | CRQ000000256055 | Muhammad Shahed
8 | 26-Aug-20 | Md. Masudur Rahman | Padma_Colo | New Link instalation | PTGCP01,PTGCP18 | Non-Service Effective | 00:00 Minute | Barisal | e.co_Barisal | CRQ000000256075 | Muhammad Shahed
9 | 2020-08-26 | Md. Masudur Rahman | DHAKA_MODERNIZATION | New Link instalation | MNLHG18,MNSRN18 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka South | CRQ000000256072 | Muhammad Shahed
10 | 2020-08-26 | Md. Masudur Rahman | DHAKA_MODERNIZATION | Capacity upgradation | MNSDR26,MNTGB03 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka South | CRQ000000256068 | Muhammad Shahed
11 | 2020-08-26 | Md. Masudur Rahman | NCCD AbisoIP | Garbage E1 Deletetion | SYBLG09,SYBLG04 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000256044 | Muhammad Shahed

## Information (hidden)
Site List | Relation | 30 Minute |  |  | Function for init.py | Project Coordinator | Service Type | Down Time | Dhaka | Barisal | Mymensingh | Kustia | Sylhet | Chittagong | Comilla | Khulna | Noakhali | Rajshahi | Rangpur
DHGUL10 | DHGUL10 | 2020-07-04 | 9:00 | 07/04/2020 9:00 AM | get_start_time | Md. Masudur Rahman | Service Effective | 00:00 Minute | e.co_Dhaka Metro | e.co_Barisal | e.co_Mymensingh | e.co_Kustia | e.co_Sylhet | e.co_CTG_Metro | e.co_Comilla | e.co_Khulna | e.co_Noakhali | e.co_Rajshahi | e.co_Rangpur
DHGUL74 | DHGUL10,DHGUL74 |  | 11:00 | 07/04/2020 11:00 AM | get_start_downtime | KM Jiaul Islam Jibon | Non-Service Effective | 00:30 Minute | e.co_Dhaka North |  |  |  |  | e.co_CTG_North
DHGUL76 | DHGUL10,DHGUL74,DHGUL76 |  | 11:40 | 07/04/2020 11:40 AM | get_end_downtime | Md. Mafuzur Rahman |  | 00:45 Minute | e.co_Dhaka South |  |  |  |  | e.co_CTG_South
DHMRP28 | DHGUL10,DHGUL74,DHGUL76,DHMRP28 |  | 17:00 | 07/04/2020 5:00 PM | get_activity_hour | Md. Shahadat Hossain |  | 01:00 Hour
DHPLB19 | DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19 |  | 18:00 | 07/04/2020 6:00 PM | get_end_time | Prodip Biswas |  | 02:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19, |  |  |  |  | Md. Rashekul Islam Raju |  | 03:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19,, | [6 empty] | 04:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19,,, | [6 empty] | 06:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19,,,, |  |  |  |  | Robi PM |  | 08:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19,,,,, |  |  |  |  | Muhammad Shahed
Ripan Kumar
Md. Walee Zaman
Faisal Mahmud Fuad
Shahriar Mahbub
Sumon Kumar Biswas