## Change_List
No | Date | Project Coordinator | Project Name | Change Activity | Impact Site List | Service Type | Down Time | Site Group | Commercial Zone | NCR Number | Change Manager
1 | 05-Sep-20 | Md. Shahadat Hossain | Padma_Colo | CPRI Cable & RRU Swap 1/1 | SNCTK27 | Service Effective | 04:00 Hour | Sylhet | e.co_Sylhet | CRQ000000259415 | K.M Khairul Bashar
2
3 | 05-Sep-20 | Prodip Biswas | L18CellAdd, Y2020 | GSM & RRU Swap 1/1 | SNCTK19,SNCTK20 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000259387 | Sumon Kumar Biswas
4 | 05-Sep-20 | Prodip Biswas | L18CellAdd, Y2020 | GSM & RRU Swap 1/1 | GPKLG26 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka North | CRQ000000259389 | Sumon Kumar Biswas
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Sheet1
No | Date | Project Coordinator | Project Name | Change Activity | Impact Site List | Service Type | Down Time | Site Group | Commercial Zone | NCR Number | Change Manager
1 | 03-Sep-20 | Md. Rashekul Islam Raju | Project 964 | GSM Antenna Optimization | SYBNB05, SYZKG15 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000258630 | Muhammad Shahed
2 | 03-Sep-20 | Md. Shahadat Hossain | Padma Colocation Project | CPRI Cable & RRU Swap | SNDRI05,SNDRI10,SNCTK16,SNCTK27,SNSDR18 | Service Effective | 04:00 Hour | Sylhet | e.co_Sylhet | CRQ000000258633 | Muhammad Shahed
3 | 03-Sep-20 | Prodip Biswas | L18CellAdd, Y2020 | GSM & RRU Swap | SYSDR32,SNCTK23 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000258636 | Sumon Kumar Biswas
4 | 03-Sep-20 | Prodip Biswas | L18CellAdd, Y2020 | GSM & RRU Swap | GPKLG30 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka North | CRQ000000258639 | Sumon Kumar Biswas
5 | 03-Sep-20 | KM Jiaul Islam Jibon | Dhaka-Modernization | FE Configuration | DHDHN45,DHKHL47,DHKHLA0,DHPTN29,DHRMN04,DHRMN16,DHRMN26,DHBDD78,DHGULF5,DHMDP01 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000258643 | Muhammad Shahed
6 | 03-Sep-20 | KM Jiaul Islam Jibon | Dhaka-Modernization | FE Configuration | MGGHR11,MGSBL11,MGSTR01,MNLHG02,MNLHG17,GPSDRS5,MNSDR46 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka North | CRQ000000258648 | Muhammad Shahed
7 | 03-Sep-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | New Link installation | MGSNG08,DHKGNT1 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka North | CRQ000000258651 | Muhammad Shahed
6 | 03-Sep-20 | Md. Masudur Rahman | NCCD AbisoIP | Garbage E1 Deletetion | SYGLP01,SYBLG09,SYBLG04 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000258654 | Muhammad Shahed
| 03-Sep-20 | Md. Masudur Rahman | CEP | DCN Configure | DHTEJ15,DHTEJ07 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000258658 | Muhammad Shahed
| 03-Sep-20 | Md. Masudur Rahman | Padma_Colo | New Link installation | BHCFN02,BHCFN26,BHLMN01,BHLMN15 | Non-Service Effective | 00:00 Minute | Barisal | e.co_Barisal | CRQ000000258661 | Muhammad Shahed
11 | 03-Sep-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | New Link installation | MNLHG18,MNSRN18 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka South | CRQ000000258665 | Muhammad Shahed
| 03-Sep-20 | Md. Masudur Rahman | NCCD AbisoIP | Traffic Check for Traffic shiftng | HGNBG28,HGNBG08 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000258668 | Muhammad Shahed
| 03-Sep-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | HW upgradation | GPSRP66,GPSDRO4,GPSDR86,GPSDR42 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka North | CRQ000000258672 | Muhammad Shahed
14 | 18-Aug-20 | Md. Masudur Rahman | NCCD AbisoIP | MW Link Dismantle Link ID: SY13E10200 Link Name: SYBNB22-SYBNB30 DCN Impact: SYBNB22-EMTN-01 | SYBNB22,SYBNB30 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000252871 | Muhammad Shahed
15 | 18-Aug-20 | Md. Masudur Rahman | NCCD AbisoIP | MW Link Dismantle Link ID: SY13H17220 Link Name: SYBNB15-SYBNB12 DCN Impact: SYBNB12-HRTN-01,SYBNB15-HRTN-01 | SYBNB15,SYBNB12 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000252874 | Muhammad Shahed
16 | 18-Aug-20 | Md. Masudur Rahman | NCCD AbisoIP | MW Link Dismantle Link ID: SY11H17368 Link Name: HGNBG30-HGNBG03 DCN Impact: HGNBG03-HRTN-05,HGNBG30-HRTN-05 | HGNBG30,HGNBG03 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000252876 | Muhammad Shahed
17 | 18-Aug-20 | Md. Masudur Rahman | NCCD AbisoIP | MW Link Dismantle Link ID: SY13H17174 Link Name:HGNBG04-HGNBG03 DCN Impact: HGNBG04-HRTN-01,HGNBG03-HRTN-06 | HGNBG04,HGNBG03 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000252879 | Muhammad Shahed
18 | 18-Aug-20 | Md. Masudur Rahman | NCCD AbisoIP | MW Link Dismantle Link ID: SY07S00421 Link Name:HGNBG03-SYBLG04 DCN Impact: No Data Found | HGNBG03,SYBLG04 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000252884 | Muhammad Shahed
No | Date | Project Coordinator | Project Name | Change Activity | Impact Site List | Service Type | Down Time | Site Group | Commercial Zone | NCR Number | Change Manager
1 | 02-Sep-20 | Md. Rashekul Islam Raju | Project 964 | GSM Antenna Optimization | SYBNB05,SYGWN03, SYZKG15 | Service Effective | 00:45 Minute | Sylhet | e.co_Sylhet | CRQ000000258233 | Muhammad Shahed
2 | 02-Sep-20 | Prodip Biswas | L18CellAdd, Y2020 | GSM & RRU Swap | SYSDR32,SNCTK23 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000258237 | Sumon Kumar Biswas
3 | 02-Sep-20 | Prodip Biswas | L18CellAdd, Y2020 | GSM & RRU Swap | GPKLG26 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka North | CRQ000000258241 | Sumon Kumar Biswas
4 | 02-Sep-20 | Md. Shahadat Hossain | Padma Colocation Project | CPRI Cable & RRU Swap | SNDRI02,SNDRI05,SNDRI10,SNCTK16,SNCTK27,SNSDR18 | Service Effective | 04:00 Hour | Sylhet | e.co_Sylhet | CRQ000000258245 | Muhammad Shahed
6 | 02-Sep-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | New Link installation | MGSNG08,DHKGNT1 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka North | CRQ000000258251 | Muhammad Shahed
7 | 02-Sep-20 | Md. Masudur Rahman | NCCD AbisoIP | Garbage E1 Deletetion | SYGLP01,SYBLG09,SYBLG04 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000258256 | Muhammad Shahed
8 | 02-Sep-20 | Md. Masudur Rahman | CEP | New Link installation | DHTEJ15,DHTEJ07 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000258260 | Muhammad Shahed
9 | 02-Sep-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | Rectification | TNSKP18,TNMZP48 | Non-Service Effective | 00:00 Minute | Mymensingh | e.co_Mymensingh | CRQ000000258262 | Muhammad Shahed
10 | 02-Sep-20 | Md. Masudur Rahman | Padma_Colo | New Link installation | BHCFN02,BHCFN26,BHLMN01,BHLMN15 | Non-Service Effective | 00:00 Minute | Barisal | e.co_Barisal | CRQ000000258266 | Muhammad Shahed
11 | 02-Sep-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | New Link installation | MNLHG18,MNSRN18 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka South | CRQ000000258270 | Muhammad Shahed
12 | 02-Sep-20 | Md. Masudur Rahman | NCCD AbisoIP | Traffic Check for Traffic shiftng | HGNBG28,HGNBG08 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000258272 | Muhammad Shahed
13 | 02-Sep-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | HW upgradation | GPSDR86,GPSDR42 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka North | CRQ000000258276 | Muhammad Shahed
14 | 02-Sep-20 | KM Jiaul Islam Jibon | Dhaka-Modernization | FE Configuration | DHDHN45,DHKHL47,DHKHLA0,DHPTN29,DHRMN04,DHRMN16,DHRMN26,DHBDD78,DHGULF5,DHMDP01 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000258283 | Muhammad Shahed
15 | 02-Sep-20 | KM Jiaul Islam Jibon | Dhaka-Modernization | FE Configuration | MGGHR11,MGSBL11,MGSTR01,MNLHG02,MNLHG17,GPSDRS5,MNSDR46,DHSVRG5 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka North | CRQ000000258286 | Muhammad Shahed

## Information (hidden)
Site List | Relation | 30 Minute |  | Function for init.py | Project Coordinator | Service Type | Down Time | Dhaka | Barisal | Mymensingh | Kustia | Sylhet | Chittagong | Comilla | Khulna | Noakhali | Rajshahi | Rangpur
DHGUL10 |  | 2020-07-04 | 9:00 | get_start_time | Md. Masudur Rahman | Service Effective | 00:00 Minute | e.co_Dhaka Metro | e.co_Barisal | e.co_Mymensingh | e.co_Kustia | e.co_Sylhet | e.co_CTG_Metro | e.co_Comilla | e.co_Khulna | e.co_Noakhali | e.co_Rajshahi | e.co_Rangpur
DHGUL74 |  |  | 11:00 | get_start_downtime | KM Jiaul Islam Jibon | Non-Service Effective | 00:30 Minute | e.co_Dhaka North |  |  |  |  | e.co_CTG_North
DHGUL76 |  |  | 11:40 | get_end_downtime | Md. Mafuzur Rahman |  | 00:45 Minute | e.co_Dhaka South |  |  |  |  | e.co_CTG_South
DHMRP28 |  |  | 17:00 | get_activity_hour | Md. Shahadat Hossain |  | 01:00 Hour
DHPLB19 |  |  | 18:00 | get_end_time | Prodip Biswas |  | 02:00 Hour
[5 empty] | Md. Rashekul Islam Raju |  | 03:00 Hour
04:00 Hour
06:00 Hour
[5 empty] | Robi PM |  | 08:00 Hour
Muhammad Shahed
Ripan Kumar
Md. Walee Zaman
Faisal Mahmud Fuad
Shahriar Mahbub
Sumon Kumar Biswas