## Change_List
No | NCR Date | Project Coordinator | Project Name | Change Activity | Impact Site List | Service Type | Down Time | Site Group | Commercial Zone | NCR Number | Change Manager
1 | 10-Aug-20 | Md. Masudur Rahman | Operational | HW _Upgrade | MBKLR30,MBKLR27 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet |  | Muhammad Shahed
2 | 29-Jul-20 | Md. Masudur Rahman | Legacy | New Link instalation | NGSNG07,NGSNG57 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka South | CRQ000000248827 | Muhammad Shahed
3 | 29-Jul-20 | Md. Masudur Rahman | Operational | PAT activity | SYSDRB6,SYSDRA8 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000248831 | Muhammad Shahed
4 | 29-Jul-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | RAU Release Udate | DHKHL05,DHKHL74 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000248835 | Muhammad Shahed
5 | 29-Jul-20 | Md. Masudur Rahman | NCCD AbisoIP | Dismantle activity | SYGWN10,SYGWN13,SYGWN05,SYGWN01,SYSDR34 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000248840 | Muhammad Shahed
6 | 28-Jul-20 | Md. Masudur Rahman | Pinacle | MMU changed | DHADB03,DHADB20 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000248532 | Muhammad Shahed
7 | 28-Jul-20 | Md. Masudur Rahman | CEP | PAT activity | DHLLB15,DHKTL18 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000248535 | Muhammad Shahed
8 | 28-Jul-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | RAU Release Udate | DHKHL05,DHKHL74 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000248538 | Muhammad Shahed
9 | 28-Jul-20 | Md. Masudur Rahman | CEP | New Link instalation | DHTEJ07,DHTEJ15,DHKTL22 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000248543 | Muhammad Shahed
10 | 28-Jul-20 | Md. Masudur Rahman | Padma_Colo | Traffic Shifting 1/1 | HGSDR24,HGSDR04,HGBNC04,HGNBG05 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000248545 | Muhammad Shahed
11
12
13
14
15
16
17
18
19
20

## Sheet1
No | NCR Date | Project Coordinator | Project Name | Change Activity | Impact Site List | Service Type | Down Time | Site Group | Commercial Zone | NCR Number | Change Manager
1 | 23-Jul-20 | Md. Masudur Rahman | Padma_Colo | Traffic shifting 1/1 | SYBNB22,SYBNB26,HGNBG08,HGNBG28 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000246920 | Muhammad Shahed
2 | 23-Jul-20 | Md. Masudur Rahman | Operational | MMU changed | HGNBG03,HGNBG07 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000246922 | Muhammad Shahed
3 | 23-Jul-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | Capacity Upgaradation | MGSNG05,MGSNG06 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka North | CRQ000000246927 | Muhammad Shahed
4 | 23-Jul-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | Rectifiacation | DHKHL05,DHDHL74 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000246930 | Muhammad Shahed
5 | 23-Jul-20 | Md. Masudur Rahman | Legacy | New Link instalation | DHSVR12,DHSVR23 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka North | CRQ000000246938 | Muhammad Shahed
6 | 23-Jul-20 | Md. Masudur Rahman | Operational | New Link instalation | HGSDR04,HGSDR24 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000246942 | Muhammad Shahed
7 | 23-Jul-20 | Md. Masudur Rahman | L900 | New CPRI install with Cell add to L900 | DHSBG11,DHSBG28 | Service Effective | 03:00 Hour | Dhaka | e.co_Dhaka Metro | CRQ000000246946 | Shahriar Mahbub
8 | 23-Jul-20 | Md. Masudur Rahman | Operational | HW _Upgrade | SYSDR86,SYSDR85,SYSDRB6,SYSDRA8 | Service Effective | 01:00 Hour | Sylhet | e.co_Sylhet | CRQ000000246952 | Muhammad Shahed
9 | 23-Jul-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | PAT activity | DHBDDA7,DHBDD26 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000246959 | Muhammad Shahed
10 | 12-Jul-20 | KM Jiaul Islam Jibon | CEP_OPEX | FE Configuration + GE Shifting | DHDHN34,DHDHN32 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000242615 | Muhammad Shahed
11 | 12-Jul-20 | KM Jiaul Islam Jibon | RING_CEP | FE Configuration + GE Shifting | SYZKG12,SYKNG06,SYZKG05 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000242618 | Muhammad Shahed
12 | 12-Jul-20 | KM Jiaul Islam Jibon | Dhaka-Modernization | FE configuration + Ping Check | DHMJH58,DHCNT48,DHHZR12,DHBDD55,DHGUL68,DHGUL11,DHGUL87 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000242622 | Muhammad Shahed
13 | 12-Jul-20 | Md. Masudur Rahman | Dhaka-Modernization | Traffic shifting | DHDHM36,DHDHM33 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka North | CRQ000000242626 | Muhammad Shahed
14 | 12-Jul-20 | Md. Masudur Rahman | Padma_Colo | New Link instalation | HGSDR05,HGSDR28,SYBNB22,SYBNB26,SYDKS04,SYDKS15 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000242631 | Muhammad Shahed
15 | 12-Jul-20 | Md. Masudur Rahman | Legacy | New Link instalation | DHSVR12,DHSVR23 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka North | CRQ000000242635 | Muhammad Shahed
16 | 12-Jul-20 | Md. Masudur Rahman | Operational | MMU & ISM6 Card changed | HGNBG03,HGNBG07,MBKLR30,MBKLR27 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000242637 | Muhammad Shahed
17 | 12-Jul-20 | Md. Masudur Rahman | Dhaka-Modernization | New Link instalation | NGARH01,NGARH26 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka South | CRQ000000242641 | Muhammad Shahed
18 | 12-Jul-20 | Md. Masudur Rahman | Padma_Colo | Traffic shifting 1/1 | SNDKS01,SNDRI01,SNDRI10 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000242646 | Muhammad Shahed
19 | 12-Jul-20 | Md. Masudur Rahman | Legacy | Dismantle activity | MNSRK16,MNSRK13 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka South | CRQ000000242649 | Muhammad Shahed
20 | 12-Jul-20 | KM Jiaul Islam Jibon | Dhaka-Modernization | FE configuration + Ping Check | MGDLP01,GPSDRC0,MNLHG11,MNSRN11,MNSRN12,MNSRN17,DHDHM09,DHSVR99 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka South | CRQ000000242651 | Muhammad Shahed
No | NCR Date | Project Coordinator | Project Name | Change Activity | Impact Site List | Service Type | Down Time | Site Group | Commercial Zone | NCR Number | Change Manager
1 | 26-Jul-20 | Md. Shahadat Hossain | Padma Colocation Project | CPRI Cable & RRU Swap | BRAMT14 | Service Effective | 04:00 Hour | Barisal | e.co_Barisal | CRQ000000247893 | Muhammad Shahed
2 | 26-Jul-20 | Md. Shahadat Hossain | Padma Colocation Project | CPRI Cable & RRU Swap | NSSBP07 | Service Effective | 04:00 Hour | Dhaka | e.co_Dhaka South | CRQ000000247897 | Muhammad Shahed
3 | 26-Jul-20 | Prodip Biswas | L18CellAdd, Y2020 | GSM & RRU Swap | BMNBG29 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000247900 | Sumon Kumar Biswas
4 | 26-Jul-20 | Prodip Biswas | L18CellAdd, Y2020 | GSM & RRU Swap | NSRPR25 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka North | CRQ000000247922 | Sumon Kumar Biswas
5 | 26-Jul-20 | Md. Masudur Rahman | Padma_Colo | Traffic shifting 1/1 | SYBNB22,SYBNB26,HGNBG08,HGNBG28 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000247928 | Muhammad Shahed
6 | 26-Jul-20 | Md. Masudur Rahman | Pinacle | MMU changed | DHMDP20,DHTEJ39,DHDHN07,DHDHN06,DHADB03,DHADB20 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000247931 | Muhammad Shahed
7 | 26-Jul-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | PAT activity | DHKHL05,DHDHL74,DHLLB15,DHKTL18,DHKTL22,DHKTL24,DHTEJ07,DHTEJ15 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000247934 | Muhammad Shahed
8 | 26-Jul-20 | Md. Masudur Rahman | Operational | PAT activity | HGSDR04,HGSDR24 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000247937 | Muhammad Shahed
9 | 26-Jul-20 | Md. Masudur Rahman | L900 | New CPRI install with Cell add to L900 | NGRPG56,NGSDR13 | Service Effective | 02:00 Hour | Dhaka | e.co_Dhaka South | CRQ000000247944 | Muhammad Shahed
10 | 26-Jul-20 | Md. Masudur Rahman | L900 | Only CPRI shifting & U900 to L900 | DHUTT10 | Service Effective | 01:00 Hour | Dhaka | e.co_Dhaka North | CRQ000000247948 | Muhammad Shahed
11 | 22-Jul-20 | Md. Rashekul Islam Raju | Project 964 | GSM Antenna Optimization | DHSVR39,GPSDR58,GPSDR17 | Service Effective | 00:45 Minute | Dhaka | e.co_Dhaka North | CRQ000000246507 | Sutipta das
12 | 22-Jul-20 | Md. Shahadat Hossain | Padma Colocation Project | CPRI Cable & RRU Swap | BHBRN09,BSMLD02,BHBRN13 | Service Effective | 04:00 Hour | Barisal | e.co_Barisal | CRQ000000246518 | Muhammad Shahed
13 | 22-Jul-20 | Md. Shahadat Hossain | Padma Colocation Project | CPRI Cable & RRU Swap | CDJBN10 | Service Effective | 04:00 Hour | Kustia | e.co_Kustia | CRQ000000246523 | Muhammad Shahed
14 | 22-Jul-20 | Md. Shahadat Hossain | Padma Colocation Project | CPRI Cable & RRU Swap | NSRPR33,NSSBP07 | Service Effective | 04:00 Hour | Dhaka | e.co_Dhaka South | CRQ000000246525 | Muhammad Shahed
15 | 22-Jul-20 | Md. Shahadat Hossain | Padma Colocation Project | CPRI Cable & RRU Swap | HGCNR13,HGCNR17 | Service Effective | 04:00 Hour | Sylhet | e.co_Sylhet | CRQ000000246529 | Muhammad Shahed