## Change_List
No | Date | Project Coordinator | Project Name | Change Activity | Impact Site List | Service Type | Down Time | Site Group | Commercial Zone | NCR Number | Change Manager
1 | 21-Sep-20 | Md. Rashekul Islam Raju | MW antenna optimization | MW antenna optimization | DHGUL11, DHGUL26, DHGUL74 | Non-Service Effective | 00:45 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000265067 | Muhammad Shahed
2 | 21-Sep-20 | Prodip Biswas | L18CellAdd, Y2020 | GSM & RRU Swap | MBKLR26, SYBLG20 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000265070 | Sumon Kumar Biswas
3 | 21-Sep-20 | Md. Masudur Rahman | NCCD AbisoIP | Rectification | SYZKG15,SYZKG01 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000265074 | Muhammad Shahed
4 | 21-Sep-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | DCN Configure | NGARH26,NGARH09,NGSNG11,NGSNG20 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka South | CRQ000000265079 | Muhammad Shahed
5 | 21-Sep-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | Rectification for XPIC allignment | TNGPL01,TNGTL27 | Service Effective | 00:30 Minute | Mymensingh | e.co_Mymensingh | CRQ000000265086 | Muhammad Shahed
6 | 21-Sep-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | Ne link installation | GPKLG05,GPSDR06,DHKHGT1,MGSNG08 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka North | CRQ000000265091 | Muhammad Shahed
7 | 21-Sep-20 | Md. Masudur Rahman | Padma_Colo | MW Dismantle activity Link ID:SY13H31786 Link Name:SYBNB22-SYBNB26 DCN Impact:SYBNB26-EMTN-01,SYBNB22-EMTN-01,SYBNB22-EMTN-01,SYBNB29-EMTN-01 DCN Path:SYBNB26-SYBNB22-SYBNB05-SYBNB29 Impact list:SYBNB22,SYBNB26 | SYBNB22,SYBNB26 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000265095 | Muhammad Shahed
8 | 21-Sep-20 | Md. Masudur Rahman | Padma_Colo | MW Dismantle activity Link ID:SY07H30739 Link Name:SNDRI01-SNDRI10 DCN Impact: SNDRI01-HRTN01,SNDRI01-HRTN02 DCN Path:SNDRI01-SNDRI10 | SNDRI01,SNDRI10 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000265099 | Muhammad Shahed
9 | 21-Sep-20 | KM Jiaul Islam Jibon | Dhaka-Modernization | FE Configuration | MGDLP08 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka North | CRQ000000265102 | Muhammad Shahed
10 | 21-Sep-20 | Md. Shahadat Hossain | CC 4G Colocation Project | GSM Antenna & RRU Swap | LXRGN14,LXRGN11,LXRPR19 | Service Effective | 04:00 Hour | Noakhali | e.co_Noakhali | CRQ000000265107 | Faisal Mahmud Fuad
11 | 21-Sep-20 | Md. Shahadat Hossain | CC 4G Colocation Project | GSM Antenna & RRU Swap | BMNBG17,BMNBG19 | Service Effective | 04:00 Hour | Comilla | e.co_Comilla | CRQ000000265113 | Faisal Mahmud Fuad
12
13
14
15
16
17
18
19
20

## Sheet1
No | Date | Project Coordinator | Project Name | Change Activity | Impact Site List | Service Type | Down Time | Site Group | Commercial Zone | NCR Number | Change Manager
1 | 20-Sep-20 | Prodip Biswas | L18CellAdd, Y2020 | GSM & RRU Swap | HGLKH02,HGBNC02,HGNBG03 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000264672 | Sumon Kumar Biswas
2 | 20-Sep-20 | Md. Shahadat Hossain | CC 4G Colocation Project | GSM Antenna & RRU Swap 1/1 | LXRGN14,LXRGN11,LXRGN33,LXRPR19 | Service Effective | 04:00 Hour | Noakhali | e.co_Noakhali | CRQ000000264675 | Faisal Mahmud Fuad
3 | 20-Sep-20 | Md. Shahadat Hossain | CC 4G Colocation Project | GSM Antenna & RRU Swap 1/1 | BMNBG17,BMNBG19,BMNBG23 | Service Effective | 04:00 Hour | Comilla | e.co_Comilla | CRQ000000264679 | Faisal Mahmud Fuad
4 | 20-Sep-20 | Md. Rashekul Islam Raju | MW antenna optimization | MW antenna optimization | DHBDD11, DHGUL66, DHKKT06 | Non-Service Effective | 00:45 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000264681 | Muhammad Shahed
5 | 20-Sep-20 | KM Jiaul Islam Jibon | Dhaka-Modernization | FE Ping Test | GPSDR76,GPSDRN0,MGSDR31,MNLHG11,MNSDR19,MNSDR28,MNSRN16,MNSRN17,GPKLK27,GPSDR61 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka North | CRQ000000264684 | Muhammad Shahed
6 | 20-Sep-20 | KM Jiaul Islam Jibon | Dhaka-Modernization | FE Ping Test | DHBDD05,DHDHN45,DHMJH47,DHPTN16,DHRMN36,DHBDD78,DHGULF5,DHMDP01,DHMDP05 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000264687 | Muhammad Shahed
7 | 20-Sep-20 | KM Jiaul Islam Jibon | Dhaka-Modernization | FE Ping Test | TNGPL06 | Non-Service Effective | 00:00 Minute | Mymensingh | e.co_Mymensingh | CRQ000000264689 | Muhammad Shahed
8 | 20-Sep-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | Rectification | TNGPL01,TNGTL27 | Service Effective | 00:30 Minute | Mymensingh | e.co_Mymensingh | CRQ000000264698 | Muhammad Shahed
9 | 20-Sep-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | DCN Configure | NGARH26,NGARH09 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka South | CRQ000000264702 | Muhammad Shahed
10 | 20-Sep-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | Ne link installation | GPKLG05,GPSDR06,DHKHGT1,MGSNG08 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka North | CRQ000000264708 | Muhammad Shahed
11 | 20-Sep-20 | Md. Masudur Rahman | DHAKA_MODERNIZATION | Traffic shifting 1/1 Link ID:DH07E18275 Link Name:MNLHG18-MNSRN18 DCN Impact:MNLHG18-EMTN-02,MNLHG18-EMTN-01,MNLHG02-EMTN-01,MNLHG08-EMTN-01,MNLHG18-EMTN-03,MNSRN18-EMTN-02 DCN Path:MNSRN18-MNLHG18-MNLHG02,MNLHG08 Impact List:MNLHG18,MNSRN18 | MNLHG18,MNSRN18 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka South | CRQ000000264711 | Muhammad Shahed
12 | 20-Sep-20 | Md. Masudur Rahman | Padma_Colo | Link ID:SY07H30744 Link Name:SNDKS01-SNDRI01 DCN Impact:SNDKS01-HRTN-01,SNDKS01-HRTN-02,SNDKS01-HRTN-03,SNDRI01-HRTN01 DCN Path:SNJML02-SNDKS01-SNDRI05 Impact list:SNDKS01,SNDRI01,SNDRI10 | SNDKS01,SNDRI01 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000264715 | Muhammad Shahed
13 | 20-Sep-20 | Md. Masudur Rahman | Padma_Colo | MW Dismantle activity Link ID:SY07H30739 Link Name:SNDRI01-SNDRI10 DCN Impact: SNDRI01-HRTN01,SNDRI01-HRTN02 DCN Path:SNDRI01-SNDRI10 | SNDRI01,SNDRI10 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000264718 | Muhammad Shahed

## Information (hidden)
Site List | Relation | 30 Minute |  | Function for init.py | Project Coordinator | Service Type | Down Time | Dhaka | Barisal | Mymensingh | Kustia | Sylhet | Chittagong | Comilla | Khulna | Noakhali | Rajshahi | Rangpur
DHGUL10 |  | 2020-07-04 | 9:00 | get_start_time | Md. Masudur Rahman | Service Effective | 00:00 Minute | e.co_Dhaka Metro | e.co_Barisal | e.co_Mymensingh | e.co_Kustia | e.co_Sylhet | e.co_CTG_Metro | e.co_Comilla | e.co_Khulna | e.co_Noakhali | e.co_Rajshahi | e.co_Rangpur
DHGUL74 |  |  | 11:00 | get_start_downtime | KM Jiaul Islam Jibon | Non-Service Effective | 00:30 Minute | e.co_Dhaka North |  |  |  |  | e.co_CTG_North
DHGUL76 |  |  | 11:40 | get_end_downtime | Md. Mafuzur Rahman |  | 00:45 Minute | e.co_Dhaka South |  |  |  |  | e.co_CTG_South
DHMRP28 |  |  | 17:00 | get_activity_hour | Md. Shahadat Hossain |  | 01:00 Hour
DHPLB19 |  |  | 18:00 | get_end_time | Prodip Biswas |  | 02:00 Hour
[5 empty] | Md. Rashekul Islam Raju |  | 03:00 Hour
04:00 Hour
06:00 Hour
[5 empty] | Robi PM |  | 08:00 Hour
Muhammad Shahed
Ripan Kumar
Md. Walee Zaman
Faisal Mahmud Fuad
Shahriar Mahbub
Sumon Kumar Biswas