## Change_List
No | Date | Project Coordinator | Project Name | Change Activity | Impact Site List | Service Type | Down Time | Site Group | Commercial Zone | NCR Number | Change Manager
1 | 2020-09-21 | Md. Rashekul Islam Raju | MW antenna optimization | MW antenna optimization | DHGUL11, DHGUL26, DHGUL74 | Non-Service Effective | 00:45 Minute | Dhaka | e.co_Dhaka Metro |  | Muhammad Shahed
2 | 2020-09-21 | Prodip Biswas | L18CellAdd, Y2020 | GSM & RRU Swap | MBKLR26, SYBLG20 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet |  | Sumon Kumar Biswas
3 | 2020-09-21 | Md. Masudur Rahman | NCCD AbisoIP | Rectification | SYZKG15,SYZKG01 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet |  | Muhammad Shahed
4 | 2020-09-21 | Md. Masudur Rahman | DHAKA_MODERNIZATION | DCN Configure | NGARH26,NGARH09,NGSNG11,NGSNG20 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka South |  | Muhammad Shahed
5 | 2020-09-21 | Md. Masudur Rahman | DHAKA_MODERNIZATION | Rectification for XPIC allignment | TNGPL01,TNGTL27 | Service Effective | 00:30 Minute | Mymensingh | e.co_Mymensingh |  | Muhammad Shahed
6 | 2020-09-21 | Md. Masudur Rahman | DHAKA_MODERNIZATION | Ne link installation | GPKLG05,GPSDR06,DHKHGT1,MGSNG08 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka North |  | Muhammad Shahed
7 | 2020-09-21 | Md. Masudur Rahman | Padma_Colo | MW Dismantle activity Link ID:SY13H31786 Link Name:SYBNB22-SYBNB26 DCN Impact:SYBNB26-EMTN-01,SYBNB22-EMTN-01,SYBNB22-EMTN-01,SYBNB29-EMTN-01 DCN Path:SYBNB26-SYBNB22-SYBNB05-SYBNB29 Impact list:SYBNB22,SYBNB26 | SYBNB22,SYBNB26 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet |  | Muhammad Shahed
8 | 2020-09-21 | Md. Masudur Rahman | Padma_Colo | MW Dismantle activity Link ID:SY07H30739 Link Name:SNDRI01-SNDRI10 DCN Impact: SNDRI01-HRTN01,SNDRI01-HRTN02 DCN Path:SNDRI01-SNDRI10 | SNDRI01,SNDRI10 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet |  | Muhammad Shahed
9 | 2020-09-21 | KM Jiaul Islam Jibon | Dhaka-Modernization | FE Configuration | MGDLP08 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka North |  | Muhammad Shahed
10 | 2020-09-21 | Md. Shahadat Hossain | CC 4G Colocation Project | GSM Antenna & RRU Swap | LXRGN14,LXRGN11,LXRPR19 | Service Effective | 04:00 Hour | Noakhali | e.co_Noakhali |  | Faisal Mahmud Fuad
11 | 2020-09-21 | Md. Shahadat Hossain | CC 4G Colocation Project | GSM Antenna & RRU Swap | BMNBG17,BMNBG19 | Service Effective | 04:00 Hour | Comilla | e.co_Comilla |  | Faisal Mahmud Fuad
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Formulas:
Date = [1]!Table1[[#This Row],[Date]]

## Information (hidden)
Site List | Relation | 30 Minute |  |  | Function for init.py | Project Coordinator | Service Type | Down Time | Dhaka | Barisal | Mymensingh | Kustia | Sylhet | Chittagong | Comilla | Khulna | Noakhali | Rajshahi | Rangpur
DHGUL10 | DHGUL10 | 2020-07-04 | 9:00 | 07/04/2020 9:00 AM | get_start_time | Md. Masudur Rahman | Service Effective | 00:00 Minute | e.co_Dhaka Metro | e.co_Barisal | e.co_Mymensingh | e.co_Kustia | e.co_Sylhet | e.co_CTG_Metro | e.co_Comilla | e.co_Khulna | e.co_Noakhali | e.co_Rajshahi | e.co_Rangpur
DHGUL74 | DHGUL10,DHGUL74 |  | 11:00 | 07/04/2020 11:00 AM | get_start_downtime | KM Jiaul Islam Jibon | Non-Service Effective | 00:30 Minute | e.co_Dhaka North |  |  |  |  | e.co_CTG_North
DHGUL76 | DHGUL10,DHGUL74,DHGUL76 |  | 11:40 | 07/04/2020 11:40 AM | get_end_downtime | Md. Mafuzur Rahman |  | 00:45 Minute | e.co_Dhaka South |  |  |  |  | e.co_CTG_South
DHMRP28 | DHGUL10,DHGUL74,DHGUL76,DHMRP28 |  | 17:00 | 07/04/2020 5:00 PM | get_activity_hour | Md. Shahadat Hossain |  | 01:00 Hour
DHPLB19 | DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19 |  | 18:00 | 07/04/2020 6:00 PM | get_end_time | Prodip Biswas |  | 02:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19, |  |  |  |  | Md. Rashekul Islam Raju |  | 03:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19,, | [6 empty] | 04:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19,,, | [6 empty] | 06:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19,,,, |  |  |  |  | Robi PM |  | 08:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19,,,,, |  |  |  |  | Muhammad Shahed
Ripan Kumar
Md. Walee Zaman
Faisal Mahmud Fuad
Shahriar Mahbub
Sumon Kumar Biswas