## Change_List
No | Date | Project Coordinator | Activity Summary & Project Name | Change Activity | Impact Site List | Service Type | Down Time | Commercial Zone | NCR Number | Change Manager
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74

## Sheet1
No | Date | Project Coordinator | Activity Summary & Project Name | Change Activity | Impact Site List | Service Type | Down Time | Commercial Zone | NCR Number | Change Manager
1 | 05-May-21 | Md. Masudur Rahman_01841122536 | Capacity Management | Rectification | BSWZP06,BSWZP07 | Non-Service Effective | 00:00 Minute | e.co_Barisal | CRQ000000342780 | Muhammad Shahed
2 | 05-May-21 | Md. Masudur Rahman_01841122536 | 4G_Colo | Snag Clear | BSSDR37,BSSDR21 | Non-Service Effective | 00:00 Minute | e.co_Barisal | CRQ000000342783 | Muhammad Shahed
3 | 05-May-21 | Md. Masudur Rahman_01841122536 | U21 to L21 | License install 1/1 | DHSBB28,DHSBB38,DHDHN24,DHDHN14 | Service Effective | 00:30 Minute | e.co_Dhaka Metro | CRQ000000342785 | Muhammad Shahed
4 | 05-May-21 | Md. Masudur Rahman_01841122536 | Dhaka Leadership | License install 1/1 | DHGUL76,DHGUL03 | Service Effective | 00:30 Minute | e.co_Dhaka Metro | CRQ000000342787 | Muhammad Shahed
5 | 05-May-21 | Md. Masudur Rahman_01841122536 | Dhaka Leadership | HW_upgrade 1/1 | DHTEJ22,DHTEJ03,DHTEJ31,DHTEJ04,DHTIA51,DHTIA02 | Service Effective | 00:30 Minute | e.co_Dhaka North | CRQ000000342794 | Muhammad Shahed
6 | 05-May-21 | Md. Shahadat Hossain_01847188945 | CC Modernization | DUG & DUW Swap | CXSDR20 | Service Effective | 00:45 Minute | e.co_CTG_South | CRQ000000342761 | Muhammad Shahed
7 | 05-May-21 | Md. Shahadat Hossain_01847188945 | CC Modernization | DUG & DUW Swap | CXSDR52 | Service Effective | 00:45 Minute | e.co_CTG_South | CRQ000000342763 | Muhammad Shahed
8 | 05-May-21 | Md. Shahadat Hossain_01847188945 | CC Modernization | DUG & DUW Swap | CXSDR72 | Service Effective | 00:45 Minute | e.co_CTG_South | CRQ000000342769 | Muhammad Shahed
9 | 05-May-21 | Md. Masudur Rahman_01841122536 | Dhaka Leadership | HW_upgrade 1/1 | MGHRM04,MGHRM02,MGGHR12,MGGHR17 | Service Effective | 00:30 Minute | e.co_Dhaka North | CRQ000000342806 | Muhammad Shahed
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33

## Information (hidden)
Site List | Relation | 30 Minute |  |  | Function for init.py | Project Coordinator | Service Type | Down Time | Dhaka | Barisal | Mymensingh | Kustia | Sylhet | Chittagong | Comilla | Khulna | Noakhali | Rajshahi | Rangpur
DHGUL10 | DHGUL10 | 2020-07-04 | 9:00 | 07/04/2020 9:00 AM | get_start_time | Md. Masudur Rahman | Service Effective | 00:00 Minute | e.co_Dhaka Metro | e.co_Barisal | e.co_Mymensingh | e.co_Kustia | e.co_Sylhet | e.co_CTG_Metro | e.co_Comilla | e.co_Khulna | e.co_Noakhali | e.co_Rajshahi | e.co_Rangpur
DHGUL74 | DHGUL10,DHGUL74 |  | 11:00 | 07/04/2020 11:00 AM | get_start_downtime | KM Jiaul Islam Jibon | Non-Service Effective | 00:30 Minute | e.co_Dhaka North |  |  |  |  | e.co_CTG_North
DHGUL76 | DHGUL10,DHGUL74,DHGUL76 |  | 11:40 | 07/04/2020 11:40 AM | get_end_downtime | Md. Mafuzur Rahman |  | 00:45 Minute | e.co_Dhaka South |  |  |  |  | e.co_CTG_South
DHMRP28 | DHGUL10,DHGUL74,DHGUL76,DHMRP28 |  | 17:00 | 07/04/2020 5:00 PM | get_activity_hour | Md. Shahadat Hossain |  | 01:00 Hour
DHPLB19 | DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19 |  | 18:00 | 07/04/2020 6:00 PM | get_end_time | Prodip Biswas |  | 02:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19, |  |  |  |  | Md. Rashekul Islam Raju |  | 03:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19,, | [6 empty] | 04:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19,,, | [6 empty] | 06:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19,,,, |  |  |  |  | Robi PM |  | 08:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19,,,,, |  |  |  |  | Muhammad Shahed
Ripan Kumar
Md. Walee Zaman
Faisal Mahmud Fuad
Shahriar Mahbub
Sumon Kumar Biswas