## Change_List
No | Date | Project Coordinator | Project Name | Change Activity | Impact Site List | Service Type | Down Time | Site Group | Commercial Zone | NCR Number | Change Manager
1 | 04-Nov-20 | Md. Rashekul Islam Raju_01841133472 | Y2020 Capacity Expansion Cell Split | GSM antenna Swap by10Port ANT | NGSDRM0,NGSNG63, NGSNG68 | Service Effective | 00:45 Minute | Dhaka | e.co_Dhaka South | CRQ000000280769 | Muhammad Shahed
2 | 04-Nov-20 | Md. Rashekul Islam Raju_01841133472 | GSM antenna optimization | GSM antenna Swap | DHTIA01 | Service Effective | 00:45 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000280772 | Muhammad Shahed
3 | 04-Nov-20 | Prodip Biswas_01841133479 | L18CellAdd, Y2020 | Jumper Cable Change 1/1 | BMJRI14, BMNNG14, BMASG05, BMSRL10 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000280774 | Sumon Kumar Biswas
4 | 04-Nov-20 | Prodip Biswas_01841133479 | L18CellAdd, Y2020 | Jumper Cable Change 1/1 | BMJRI14, BMNNG14, BMASG05, BMSRL10 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000280777 | Sumon Kumar Biswas
5 | 04-Nov-20 | Sobuz Ahmed_01841122538 | NCCD AbisoIP | E1 deletion & Collect BTS Cable | SYBNB21,SYBNB30,SYBNB34 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000280780 | Muhammad Shahed
6 | 04-Nov-20 | Sobuz Ahmed_01841122538 | NCCD AbisoIP | E1 deletion & Collect BTS Cable | SYSDRD2,SYSDRD3,SYSDRB8,SYSDRA2 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000280782 | Muhammad Shahed
7 | 04-Nov-20 | Prodip Biswas_01841133479 | 2G Colocation | GSM Swap 1/1 | CMSDRA2 | Service Effective | 00:30 Minute | Comilla | e.co_Comilla | CRQ000000280787 | Faisal Mahmud Fuad
8 | 04-Nov-20 | KM Jiaul Islam Jibon_01847188948 | BP 2020 Rollout | FE Configuration & Electrical Patching | BHLMN15,PTDMN01 | Non-Service Effective | 00:00 Minute | Barisal | e.co_Barisal | CRQ000000280790 | Muhammad Shahed
9 | 04-Nov-20 | KM Jiaul Islam Jibon_01847188948 | NCCD AbisoIP P3 | FE Configuration & Electrical Patching | HGMDB23,SYBLG02,SYBNB33,SYJNT03 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000280792 | Muhammad Shahed
10 | 04-Nov-20 | KM Jiaul Islam Jibon_01847188948 | NCCD AbisoIP P3 | FE Configuration & Electrical Patching | MYFLP03,MYISG01/MYISG17 | Non-Service Effective | 00:00 Minute | Mymensingh | e.co_Mymensingh | CRQ000000280794 | Muhammad Shahed
11 | 04-Nov-20 | KM Jiaul Islam Jibon_01847188948 | BP 2020 Rollout | Remote FE Configuration | MDSHB32,SPDMD11,NSSDR70,HGLKH08,BMSRL27,JSMNR23,JSMNR21,SYJNT20,BMSDR98 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000280796 | K.M Khairul Bashar
12 | 04-Nov-20 | Md. Shafiqur Rahman_01841122531 | Relocation | RAU change | DHSBG28 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000280799 | Muhammad Shahed
13 | 04-Nov-20 | Md. Masudur Rahman_01841122536 | DHAKA_MODERNIZATION | PAT activity | NKKND02,MYISG02 | Service Effective | 00:30 Minute | Mymensingh | e.co_Mymensingh | CRQ000000280902 | Muhammad Shahed
14 | 04-Nov-20 | Md. Masudur Rahman_01841122536 | Padma_Colo | Rectification 1/1 | SYKNG05,SYSDR26,SYJNT03,SYJNT08,SYJNT02,SYBNB42 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000280904 | Muhammad Shahed
15 | 04-Nov-20 | Md. Masudur Rahman_01841122536 | Finito | Rectification | DHDHN41,DHTEJ23,DHTIA09,DHRMN05 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000280907 | Muhammad Shahed
16 | 04-Nov-20 | Md. Masudur Rahman_01841122536 | NCCD AbisoIP | Return Dismantle Materials | SYSDRD4,SYSDR34,SYGWN03,SYGWN05,SYJNT03,SYJNT08,SYGWN01,SYDKS28,SYGLP01 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000280909 | Muhammad Shahed
17 | 04-Nov-20 | Md. Masudur Rahman_01841122536 | NCCD AbisoIP | Slot Remove for alarm clear | SYBNB42 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000280912 | Muhammad Shahed
18 | 04-Nov-20 | Md. Masudur Rahman_01841122536 | DHAKA_MODERNIZATION | Traffic Shifting 1/1 | TNNGP12,TNKLH04,TNGPL14,TNDBR08 | Service Effective | 00:30 Minute | Mymensingh | e.co_Mymensingh | CRQ000000280914 | Muhammad Shahed
19 | 04-Nov-20 | Md. Masudur Rahman_01841122536 | DHAKA_MODERNIZATION | MW dismantle Link ID:MY18H30906 Link Name:TNNGP12-TNKLH04 DCN Impact:TNNGP12-EMTN-01 DCN Path:TNKLH04-TNNGP12 | TNNGP12,TNKLH04 | Non-Service Effective | 00:00 Minute | Mymensingh | e.co_Mymensingh | CRQ000000280916 | Muhammad Shahed
20 | 04-Nov-20 | Md. Masudur Rahman_01841122536 | Padma_Colo | Traffic shifting 1/1 | MBJRI11,MBJRI10 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000280918 | Muhammad Shahed
21 | 04-Nov-20 | Md. Masudur Rahman_01841122536 | DHAKA_MODERNIZATION | MW dismantle Link ID:MY11H30951 Link Name:TNGPL14-TNDBR08 DCN Impact:TNGPL14-EMTN-01 DCN Path:TNGPL14-TNDBR08 WO not Require Only Slot Removal | TNGPL14,TNDBR08 | Non-Service Effective | 00:00 Minute | Mymensingh | e.co_Mymensingh | CRQ000000280921 | Muhammad Shahed
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56

## Sheet1
No | Date | Project Coordinator | Project Name | Change Activity | Impact Site List | Service Type | Down Time | Site Group | Commercial Zone | NCR Number | Change Manager
1 | 01-Nov-20 | Md. Rashekul Islam Raju_01841133472 | MW antenna optimization | MW Inactive antenna Dismantle | SYBSW07,HGSDR02, SNSLA01 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000279531 | Muhammad Shahed
2 | 01-Nov-20 | Md. Rashekul Islam Raju_01841133472 | Y2020 Capacity Expansion Cell Split | GSM antenna Swap by10Port ANT | NGSDRM0,NGSDRE9 | Service Effective | 00:45 Minute | Dhaka | e.co_Dhaka South | CRQ000000279535 | Muhammad Shahed
3 | 01-Nov-20 | Md. Rashekul Islam Raju_01841133472 | GSM antenna optimization | GSM antenna Swap | MBSML01, SYZKG14 | Service Effective | 00:45 Minute | Sylhet | e.co_Sylhet | CRQ000000279538 | Muhammad Shahed
4 | 01-Nov-20 | Md. Rashekul Islam Raju_01841133472 | GSM antenna optimization | GSM antenna Swap | DHMDP09, DHNMK08 | Service Effective | 00:45 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000279541 | Muhammad Shahed
5 | 01-Nov-20 | Md. Rashekul Islam Raju_01841133472 | MW antenna optimization | MW Inactive antenna Dismantle | DHKHL26,DHKHL74 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000279545 | Muhammad Shahed
6 | 01-Nov-20 | Prodip Biswas_01841133479 | L18CellAdd, Y2020 | Jumper Cable Change 1/1 | SYZKG16, SYZKG17, MBJRI14, BMSDR24, BMASG05 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000279547 | Sumon Kumar Biswas
7 | 01-Nov-20 | Sobuz Ahmed_01841122538 | NCCD AbisoIP | E1 deletion & Collect BTS Cable | SYBSW07,SYBSW18,SYBLG21,SYBLG29 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000279550 | Muhammad Shahed
8 | 01-Nov-20 | Sobuz Ahmed_01841122538 | NCCD AbisoIP | E1 deletion & Collect BTS Cable | SYZKG02,SYZKG04,SYZKG19,SYZKG20 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000279553 | Muhammad Shahed
9 | 01-Nov-20 | Md. Shafiqur Rahman_01841122531 | Relocation | RAU Change | DHSBG28, DHSBG46 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000279555 | Muhammad Shahed
10 | 01-Nov-20 | KM Jiaul Islam Jibon_01847188948 | BP 2020 Rollout | FE Configuration & Electrical Patching | BHLMN15,PTDMN01 | Non-Service Effective | 00:00 Minute | Barisal | e.co_Barisal | CRQ000000279557 | Muhammad Shahed
11 | 01-Nov-20 | KM Jiaul Islam Jibon_01847188948 | NCCD AbisoIP P3 | FE Configuration & Electrical Patching | HGMDB23,SYBLG02,SYBNB33,SYJNT03 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000279559 | Muhammad Shahed
12 | 01-Nov-20 | KM Jiaul Islam Jibon_01847188948 | NCCD AbisoIP P3 | FE Configuration & Electrical Patching | MYFLP03,MYISG01/MYISG17 | Non-Service Effective | 00:00 Minute | Mymensingh | e.co_Mymensingh | CRQ000000279562 | Muhammad Shahed
13 | 01-Nov-20 | KM Jiaul Islam Jibon_01847188948 | BP 2020 Rollout | Remote FE Configuration | MDSHB32,SPDMD11,NSSDR70,HGLKH08,BMSRL27,JSMNR23,JSMNR21,SYJNT20,BMSDR98 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000279565 | K.M Khairul Bashar
14 | 01-Nov-20 | Forhad Hossain_01841122532 | BP 2020 Rollout | FE & DCN Configure | DHDEM39, DHSBB13 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka South | CRQ000000279568 | K.M Khairul Bashar
15 | 01-Nov-20 | Forhad Hossain_01841122532 | BP 2020 Rollout | FE & DCN Configure | BHSDR58,BHSDR47 | Non-Service Effective | 00:00 Minute | Barisal | e.co_Barisal | CRQ000000279572 | K.M Khairul Bashar
16 | 01-Nov-20 | Forhad Hossain_01841122532 | BP 2020 Rollout | FE & DCN Configure | MYFLP47, MYFLP01 | Non-Service Effective | 00:00 Minute | Mymensingh | e.co_Mymensingh | CRQ000000279574 | K.M Khairul Bashar
17 | 01-Nov-20 | Forhad Hossain_01841122532 | BP 2020 Rollout | FE & DCN Configure | SYSDRG6, SYSDR32 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000279576 | K.M Khairul Bashar
18 | 01-Nov-20 | Forhad Hossain_01841122532 | BP 2020 Rollout | FE & DCN Configure | SYGLP33, SYGLP01 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000279578 | K.M Khairul Bashar
19 | 01-Nov-20 | Forhad Hossain_01841122532 | BP 2020 Rollout | FE & DCN Configure | MBSML43,MBSML03 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000279580 | K.M Khairul Bashar
20 | 01-Nov-20 | Forhad Hossain_01841122532 | BP 2020 Rollout | FE & DCN Configure | MDKLK31,MDKLK18, MDKLK01 | Non-Service Effective | 00:00 Minute | Barisal | e.co_Barisal | CRQ000000279582 | K.M Khairul Bashar
21 | 01-Nov-20 | Forhad Hossain_01841122532 | BP 2020 Rollout | FE & DCN Configure | SYBNB60, SYBNB15 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000279586 | K.M Khairul Bashar
22 | 01-Nov-20 | Forhad Hossain_01841122532 | BP 2020 Rollout | FE & DCN Configure | SYBNB61 | Non-Service Effective | 00:00 Minute | Barisal | e.co_Barisal | CRQ000000279590 | K.M Khairul Bashar
23 | 01-Nov-20 | Forhad Hossain_01841122532 | BP 2020 Rollout | FE & DCN Configure | GPSDR3C, GPSDR26,GPSDR36 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka North | CRQ000000279594 | K.M Khairul Bashar
24 | 01-Nov-20 | Md. Masudur Rahman_01841122536 | Padma_Colo | Slot Remove for alarm clear | SYGWN03,SYJNT03,SYJNT08,SYJNT02 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000279612 | Muhammad Shahed
25 | 01-Nov-20 | Md. Masudur Rahman_01841122536 | Padma_Colo | MW Dismantle Link ID:SY18H30760 Link Name:SYJNT03-SYJNT08 DCN Impact :SYJNT03-HRTN-02,SYJNT03-HRTN-03,SYJNT08-HRTN-01 DCN Route:SYGWN03-SYJNT03-SYJNT08 WO0000000162410 | SYJNT03-SYJNT08 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000279617 | Muhammad Shahed
26 | 01-Nov-20 | Md. Masudur Rahman_01841122536 | DHAKA_MODERNIZATION | Rectification | NKKND02,MYISG02 | Service Effective | 00:30 Minute | Mymensingh | e.co_Mymensingh | CRQ000000279621 | Muhammad Shahed
27 | 01-Nov-20 | Md. Masudur Rahman_01841122536 | Padma_Colo | Rectification 1/1 | SYKNG05,SYSDR26,SYJNT03,SYJNT08 | Service Effective | 00:30 Minute | Sylhet | e.co_Sylhet | CRQ000000279626 | Muhammad Shahed
28 | 01-Nov-20 | Md. Masudur Rahman_01841122536 | DHAKA_MODERNIZATION | Dismantle Materials Return | DHDHM33,DHDHM36,MNSNG08 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka North | CRQ000000279631 | Muhammad Shahed
29 | 01-Nov-20 | Md. Masudur Rahman_01841122536 | CEP | Rectification | DHGUL58,DHTIA09,DHRMN05 | Service Effective | 00:30 Minute | Dhaka | e.co_Dhaka Metro | CRQ000000279634 | Muhammad Shahed
30 | 01-Nov-20 | Md. Masudur Rahman_01841122536 | Padma_Colo | MW Dismantle Link ID:SY07H30759 Link Name:SYJNT03-SYGWN03 DCN Impact :SYJNT03-HRTN-02,SYJNT03-HRTN-03,SYJNT08-HRTN-01,SYGWN03-HRTN-02 DCN Route:SYGWN03-SYJNT03-SYJNT08 WO0000000162410 | SYJNT03,SYGWN03 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000279639 | Muhammad Shahed
31 | 01-Nov-20 | Md. Masudur Rahman_01841122536 | NCCD AbisoIP | Slot Remove for alarm clear | SYBNB42 | Non-Service Effective | 00:00 Minute | Sylhet | e.co_Sylhet | CRQ000000279641 | Muhammad Shahed
32 | 01-Nov-20 | Md. Masudur Rahman_01841122536 | NCCD AbisoIP | DCN Configure | MYNND16,MYNND04,JPISL14,SRSDR07 | Non-Service Effective | 00:00 Minute | Mymensingh | e.co_Mymensingh | CRQ000000279644 | Muhammad Shahed
33 | 01-Nov-20 | Md. Masudur Rahman_01841122536 | DHAKA_MODERNIZATION | Dismantle Materials Return | DHKGNT1,MNLHG18,MNSRN18,MNSRK13,MNSRK16,NGSNG11,NGSNG20 | Non-Service Effective | 00:00 Minute | Dhaka | e.co_Dhaka South | CRQ000000279647 | Muhammad Shahed
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73

## Information (hidden)
Site List | Relation | 30 Minute |  |  | Function for init.py | Project Coordinator | Service Type | Down Time | Dhaka | Barisal | Mymensingh | Kustia | Sylhet | Chittagong | Comilla | Khulna | Noakhali | Rajshahi | Rangpur
DHGUL10 | DHGUL10 | 2020-07-04 | 9:00 | 07/04/2020 9:00 AM | get_start_time | Md. Masudur Rahman | Service Effective | 00:00 Minute | e.co_Dhaka Metro | e.co_Barisal | e.co_Mymensingh | e.co_Kustia | e.co_Sylhet | e.co_CTG_Metro | e.co_Comilla | e.co_Khulna | e.co_Noakhali | e.co_Rajshahi | e.co_Rangpur
DHGUL74 | DHGUL10,DHGUL74 |  | 11:00 | 07/04/2020 11:00 AM | get_start_downtime | KM Jiaul Islam Jibon | Non-Service Effective | 00:30 Minute | e.co_Dhaka North |  |  |  |  | e.co_CTG_North
DHGUL76 | DHGUL10,DHGUL74,DHGUL76 |  | 11:40 | 07/04/2020 11:40 AM | get_end_downtime | Md. Mafuzur Rahman |  | 00:45 Minute | e.co_Dhaka South |  |  |  |  | e.co_CTG_South
DHMRP28 | DHGUL10,DHGUL74,DHGUL76,DHMRP28 |  | 17:00 | 07/04/2020 5:00 PM | get_activity_hour | Md. Shahadat Hossain |  | 01:00 Hour
DHPLB19 | DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19 |  | 18:00 | 07/04/2020 6:00 PM | get_end_time | Prodip Biswas |  | 02:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19, |  |  |  |  | Md. Rashekul Islam Raju |  | 03:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19,, | [6 empty] | 04:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19,,, | [6 empty] | 06:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19,,,, |  |  |  |  | Robi PM |  | 08:00 Hour
| DHGUL10,DHGUL74,DHGUL76,DHMRP28,DHPLB19,,,,, |  |  |  |  | Muhammad Shahed
Ripan Kumar
Md. Walee Zaman
Faisal Mahmud Fuad
Shahriar Mahbub
Sumon Kumar Biswas